## Action Plan VP
FY 2027 Vehicle Parts Business Action Plan |  |  | July | [12 empty] | ■□□□ Plan made ■■□□ Started ■■■□ Started and in progress ■■■■ Completed and evaluated
DM Report | Objective | Action Point / Method | PIC | H1 | [5 empty] | H2 | [5 empty] | Progress | Comments June | Comments May | Comments
|  |  |  | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR |  | Comments may | Comments may
○ | External Sales | ITUK Don’t Lose Deal (DLOD) | JVDP | [12 empty] | □□□□ |  | ISZE will set up a draft for the management to review | bar: H1 MAY to H1 JUN; H1 SEP; H2 DEC; H2 MAR
○ | ISZE's own incentive / campaigns | Yearly incentive MOU signed | JVDP/KM | [12 empty] | ■■□□ |  | All MOU's have been signed. | MOU's are all signed off, | bar: H1 APR to H1 MAY
|  | Yearly incentive | JVDP/KM | [12 empty] | □□□□ | bar: H2 FEB to H2 MAR
|  | IUK stock scrap (€ 80K sales) | KM | [12 empty] | □□□□ | bar: H2 OCT; H2 FEB
|  | UMI stock scrap (€ 80K sales) | JVDP | bar: H2 OCT; H2 FEB
|  | UTI stock scrap (€ 80K sales) | JVDP | bar: H2 OCT; H2 FEB
|  | ITUK stock scrap (€ 140K sales) | JVDP | bar: H2 OCT; H2 FEB
|  | UTI merchandise support 5K€ | JVDP
|  | UMI support 20K€ | JVDP
|  | Brake parts campaign | JVDP | [12 empty] | □□□□ |  | See customized 6 month SPA order of IUK. | Tailor made IUK SPA for brake parts was approved | bar: H1 MAY
|  | Filters (oil, air, cabin, fuel) campaign | JVDP | [12 empty] | □□□□ | bar: H1 JUN
|  | Body parts campaign | JVDP | [12 empty] | □□□□ | bar: H1 AUG to H1 SEP
|  | BVP campaign | JVDP | [12 empty] | □□□□ | bar: H2 NOV
|  | Stock clearance | JVDP | [12 empty] | □□□□ | Stock clearance campaign will be launched in July and be valid for 3 months so DB's have time to inform the dealer network | Sales received a work file from planning dept. to do a stock clearance campaign which could reduce our stock inventory. | bar: H1 MAY to H1 AUG; H2 FEB to H2 MAR
|  | Emission parts | JVDP | [12 empty] | □□□□ | bar: H2 OCT
|  | Offer spot campaigns to customers (incl. engines, transmissions, cabs) | JVDP | [12 empty] | □□□□ |  | IUK 6 month SPA has been approved for brake parts | bar: H1 APR to H2 MAR
○ | Pricing | Do sales analysis based on DB to DLR sales data | JVDP | [12 empty] | □□□□ | bar: H1 JUL; H2 OCT; H2 JAN
○ | DB training | Create training structure (table of course contents) | BS | [12 empty] | ■■■□ | Wait for management approval | Wait for management approval | Wait for management approval | bar: H1 APR to H1 JUN
|  | Contents development | JVDP/KM | bar: H1 MAY to H2 JAN
|  | Trial | BS | [13 empty] | Training is set up for July, August and September |  | Launched end of March FY26 | bar: H1 APR; H1 JUN
|  | Rollout actual training | BS | [13 empty] | Second presentation is being prepared. First draft presented. Interest at ASC from Portugal & Hungary regarding EQ-hit training. Link has been send. Training in July. Link to training : https://forms.office.com/pages/responsepage.aspx?id=iWq0MnaF3Um94p3g8iE-yJV6ECXpY79Gt108WtczF09UMllWSk5PSDNWVVFPNlJDNkxaT0NWMllPRi4u&route=shorturl | Decision sales department to change proposed schedule and switch to trainings to promote EDI usage | First trainings done beginning of April and link was sent to DB's. Dealers from following countries already participated : • United Kingdom • Hungary • Germany • Cyprus • Norway • Iceland • Ukraine | bar: H1 APR to H2 MAR
○ | Parts competition | Create road map for parts competition | BS | [12 empty] | ■■□□ | Wait for management approval | Wait for management approval | Wait for management approval | bar: H1 APR to H1 JUN
|  | Feasibility study to incentivize DB (Survey) | Sales / IMG | bar: H1 MAY to H1 JUL
|  | Decide on trial DB for parts competition | BS/JVDP/KM | bar: H1 AUG to H1 SEP
|  | Agree on the scheme (Design) | BS/JVDP/KM | bar: H2 OCT to H2 NOV
|  | Trial | BS | bar: H2 NOV to H2 DEC
|  | Review the trial result | BS/JVDP/KM | bar: H2 JAN to H2 FEB
|  | Rollout parts competition to all DB's | BS/JVDP/KM | bar: H2 MAR
○ | Genuine parts share | Set target (incl cover ratio) | Sales / IMG | [12 empty] | ■■□□ | GPS has been calculated for all customers | ISZE has set targets for GPS for all customers upon management to review | ISZE has created an overview file with all customers with their current GPS. ISZE will advise with all customers about their GPS target. | bar: H1 APR to H1 MAY
|  | Agree on target with DB's | JVDP/KM | [13 empty] | ITUK & UTI have agreed on a GPS target which they will aim to achieve | ISZE will speak with a first set of DB's at the conference | bar: H1 JUN
|  | PMS parts promotion with IML | JVDP
|  | DB selection (ITUK) | JVDP | [15 empty] | F2F meeting with ITUK & IML to introduce the promo initiative | bar: H1 APR
|  | Target selection | JVDP | [13 empty] | ITUK target has been set | bar: H1 JUN
|  | Trial | JVDP | bar: H1 AUG to H1 SEP
|  | Results review | JVDP | bar: H2 NOV; H2 FEB
|  | PMS parts promotion with IML | JVDP | [13 empty] | ISZE will work on a parts list for reduced pricing
|  | DB selection (Petros + IUK) | JVDP | bar: H1 MAY to H1 JUN
|  | Target selection | JVDP | bar: H1 AUG
|  | Trial | JVDP | bar: H2 OCT to H2 NOV
|  | Results review | JVDP | bar: H2 JAN
|  | Roll out to other DBs | JVDP/KM | [15 empty] | FY28
|  | Decide on promotional method with DB's (which product) | JVDP/KM | bar: H1 JUL; H2 OCT; H2 JAN
|  | Review progress | Sales / IMG | bar: H1 AUG; H2 NOV; H2 FEB
|  | Review target | JVDP/KM | bar: H2 MAR
|  | Decide kickback (or not) | JVDP/KM | bar: H2 MAR
|  | Incl into DB's parts BP | JVDP/KM | bar: H2 NOV to H2 DEC
○ | KPI | Collect KPI (matrix) | Sales / IMG | [12 empty] | ■■■□ | KPI's keep on coming in a regular base. ISZE is creating an automatic receiving system via sharepont to make it easier for DB + ISZE. This is for 50% done. | KPI's keep on coming in a regular base. ISZE is thinking about creating an automotic receiving system via sharepont to make it easier for DB + ISZE. | ISZE & IMG keep on collecting KPI data. ISZE also wants to collect sales to dealer data. This will help ISZE with sales analysis wich is closer to the real demand. This will also help for replenishment purposes for planning dept. | bar: H1 APR to H2 MAR
|  | Decide and agree on action plan to improve KPI's together with the DB | JVDP/KM | [14 empty] | Selection most important KPI's for next year award | bar: H1 MAY; H1 SEP to H2 MAR
○ | Support DB's to introduce R&M / service contract program | DB's with R&M: set target for new contracts + incentive with IMG | Sales / IMG | [12 empty] | ■■□□ |  | ISZE will allign the targets for R&M of UTI & ITUK. | bar: H1 MAY to H1 JUN
|  | *Agree with ITUK on target | JVDP / IMG | [14 empty] | ISZE will contact ITUK to advise on their targets | bar: H1 MAY to H1 JUN
|  | Review progress | JVDP / IMG | bar: H1 JUN to H2 MAR
|  | Decide kickback (or not) | JVDP | bar: H2 MAR
|  | **Agree with Portugal on target | JVDP / IMG | [13 empty] | New contact @ I-Motors : further discussion in September after integration. | ISZE will discuss this during the conference with Imotors. | bar: H1 MAY to H1 JUN
|  | Review progress | JVDP / IMG | bar: H1 JUN to H2 MAR
|  | Decide kickback (or not) | JVDP | bar: H2 MAR
|  | Budget approval (Directors) for incentive | JVDP | bar: H2 MAR
|  | ***Propose and discuss with DB's w/o R&M | KM/JVDP | [14 empty] | A presentation is planned on the 4th of June to all interested DB's. | bar: H1 MAY to H2 MAR
|  | Raising awareness with DB's (incl during DLR visits) | KM/JVDP/BS | [13 empty] | Waiting for start Uematsu san for new schedule | Visit Denmark: No general program, some dealer offer limited service programs as part of independent network | Visited IUK: DLR's offer individual programs | bar: H1 APR to H1 AUG
|  | Gathering market intelligence | BS | [14 empty] | Presentation received by potential 3rd party provider to DB's. Contact with second selected potential partner to compare | Found new potential 3rd party for support; presentation end of May | bar: H1 APR; H1 SEP to H2 DEC
|  | Identifying gaps | KM/JVDP/BS | bar: H2 JAN to H2 FEB
|  | Sharing findings with IMG | Sales / IMG | bar: H2 MAR
○ | IDS | Create audit schedule | IMG | [12 empty] | ■■■□ | Schedule changed by IMG. |  | ISZE/IMG agreed on schedule | bar: H1 APR; H1 JUN
|  | Join DLR visits with IMG & IML | Sales / IMG | [14 empty] | Audit in Danmark | Audit at Midi Spain and IUK | bar: H1 APR to H1 MAY; H1 SEP to H2 NOV
|  | Review of submitted IDS | Sales / IMG | [13 empty] | Target for recommandations = September as announced by IMG on conference | Schedule aligned with IMG for visits after summer. | bar: H1 MAY to H1 JUN
|  | Award | Sales / IMG | [13 empty] | Award for IDS & KPI at ASC | Proposal for award ceremony worked out with IMG. Decision beginning June | bar: H1 MAY to H1 JUN
|  | Planning of DLR improvement activities | Sales / IMG | [13 empty] | Target for visited countries set end November | bar: H2 OCT to H2 MAR
|  | Review improvement activities | Sales / IMG | [14 empty] | First improvements made by visited DLR's | bar: H1 MAY; H2 FEB to H2 MAR
○ | Lubricant business | Support IML with business scheme | KM | [12 empty] | ■■□□ |  | ISZE will have a follow up meeting with IML in June and is gathering questionaires | Survey DB's | bar: H1 APR to H2 MAR
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R

## Action Plan ACC
FY 2027 Accessories Business Action Plan |  |  | July | [13 empty] | ■□□□ Plan made ■■□□ Started ■■■□ Started and in progress ■■■■ Completed and evaluated
[18 empty] | 2024-01-09 |  | 2023-12-08 | [7 empty] | Update 07/08 | 2026-07-07 | Update 11 June | Update 06 May
DM Report | Objective | Action Point / Method | Dead Line | PIC | H1 | [5 empty] | H2 | [5 empty] | Progress | CY 2023 DEC ACTION REPORT | Status vs Oct | CY 2023 NOV ACTION REPORT | [7 empty] | July Activity Report | June Activity Report | May Activity Report | April Activity Report (start FY27)
[5 empty] | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR |  |  |  |  | SALES TOP 5 |  |  | 2023-12-01 | Orders TOP 5 |  | 2023-12-01 |  |  |  |  | SALES TOP 5 |  | 2026-07-01 | Orders TOP 5 |  | 2026-07-01
SALES OBJECTIVES | BP FY27 Accessory sales objectives | Make sufficient efforts to meet/ exceed Action plan milestones Focus on Incremetal sales targeting: Target LCV DB's: Isuzu Ireland, Rom Auto Target CV/LCV DB's: Imotors, GZ and ISD Target CV DB: ITUK | Apr - Mar | DW | G | Y | Y | G | X | X | X | X | X | X | X | X | ■■□□ Started | TTL invoicing for Dec 2023 amounts to 298.2K EUR. Top5 Dec: V-Cross Acc (155.2K EUR) B/liners (68.8K EUR) Mats&trays (30.2K EUR); Door visors & Hood protectors (15.5K EUR) Local acc (15.5K EUR). Accessory profit (MAP) for Dec amounts to 87.4K EUR or 28.9%. Local accessories December invoicing amounts to 15.5K EUR or 5% of TTL invoice amount. | Higher profit % | TTL invoicing for Nov 2023 amounts to 263.7K EUR.. Top5: B/liners (107.5 EUR), V-Cross Acc (62.9K EUR) Mats&trays (28.3K EUR); Door visors & Hood protectors (15.3K EUR) and Side Steps & Bar (14.1K EUR). Accessory profit (MAP) for November 2023 amounts to 81.7K EUR or 30.6%. Local accessories November invoicing amounts to 10.5K EUR or 4% of TTL invoice amount. | ISD | 94.5 | K EUR |  | ISD | 51.4 | K EUR | re ISV complaint delay delivery Over fenders: No further complaint received from ISV when ISZE shared weeky updates of the allocating/invoicing QTY's Re Future demand Over fenders, other V-Cross accessories ISZE received IBX forecast and firm order for Sept-November deliveries (TTL 190x or approx € 136K) MTD sales result split; € 255K V-Cross Acc; € 149.4K B/Liner; € 115.5K local Acc and approx € 70K others | Based on IMIE production plan (April-July), ISZE shared to all DB's procuring V-Cross accessories to verify if current accessory order is fullfilling the demand. This to avoid unnecessary delay due high ISZE BO-log. For this reason ISZE requested DB to consider placing orders well in advance. Sweden (ISV) June update: Invoiced QTY 5867646500: 16pcs WIP 5867646500: 24pcs (invoiced 3/7) IAST shared Over fender WH arrival schedule until 2 July. Due to container shortage, IAST/ISZE is unable to book sufficient containers filling available stock at IAST WH. | ISZE advised ISV that due to high backorder log of 5867646500 Over fender set, to consider order alternative, matte black type Over fender set (PN 5867658270). ISV followed ISZE advise resulting: Invoiced QTY 5867658270: 50pcs Invoiced QTY 5867646500: 14pcs WIP 5867646500: 16pcs ISV BO QTY 5867646500 excl WIP: 288 pcs vs TTL of 741 pcs Due to increase orders of V-Cross accessories, ISZE has requested IAS supporting sooner delivery. | Strong MTD orders were allocated to V-Cross accessories (TTL 624x Over fenders, 509x RUP Extentions and 375x Front bumper cladding) and Bed liners (TTL 550x MY24 OR Crew, 235x UR CRW, 70x MY24 OR EXT). Positive outcome MTD sales, heavily affected by 3 product groups (Tow bar (€ 156), V-Cross (€ 108K) and Bed liner(€ 76K). Out of € 406K sales, those 3 product groups reflected sales of € 338K | IUK | 165.7 | K EUR | IBX | 136 | K EUR
| Target FY27 | Monitor monthly target and FY target 2809K EUR as well Profit Margin (23%) | Apr - Mar | DW | G | G | G | G | X | X | X | X | X | X | X | X | ■■□□ Started | CY23 invoice amount resulting to 3,475.6K EUR an substancial increase from 5+7 Sales Plan 2023. | Higher sales and profit % | [8 empty] | ISZE MTD invoice amount is highly affected by V-Cross accessories sales. Vs MTD FY26, surplus is noticeable (approx € 280K) YTD sales result of €1.6M is considerably higher vs plan. For this reason, ISZE adjusted FY27 target to €2.809K BO amount decreased to € 425K (incl orders for delivery up to Nov). Higher Margin affected by strong V-Cross Acc & B/Liner sales | YTD Invoice result amounts to: € 987.6K wiht Gross margin (MAP) of 28%. Good MAP margin are driven by V-Cross Acc sales (€ 312K) Draft MOU's for 6x DB are finished. DocuSign approval to follow early July. | YTD sales result of € 791K showing surplus of 11.5% vs FY26. YTD gross profit margin (27.7% based on MAP) is mostly driven by Apr+May V-Cross accessory sales. H1 sales plan (half of FY target) , to forse surplus due to BO amount of € 671. ISZE continue to monitor IAST delivery outlook. FY27 accessory incentives (kick back) for 6 DB'rs was approved by management. MOU's will follow (June). | Profit margin (MAP, excluding provisions) for April resulted to 26.9% (genuine and local combined) | ISD | 116.6 | K EUR | IMOT | 20.3 | K EUR
| IAST Cooperation and Efforts | Increase packaging solutions, Follow pending issues ( eg BO's and Buffer stock) and Claim handling | Apr - Mar | SZ (lead) | X | X | X | X | X | X | X | X | X | X | X | X | ■□□□ | Re Bed liners: ISZE is unable to delivery DB'ers Orders for January and February. To assist IAS, ISZE shared on monthly basis customers' orders, ttl of each PN. Same for many other accessories that are not showing stock at IAS side, Over fenders, hood protectors, RUP extentions, rubber trays, etc | Future sales affected | ISZE notice delay delivery on bed liners. IAS is unable to pull delivery forward resulting that no bed liners will be shipped between 19/11 to 22/12. FYI: ISZE PO of 12 Sept will be completely delivered on 10 December and ISZE PO of Oct 19 will be completely delivered on January 10th. This is to long for fast moving accessories. | ISV | 85.7 | K EUR |  | ISV | 43.5 | K EUR | re ISV claim Engine hood protector: ISZE scheduled 3-party meeting (7 Aug), this for IAST to explain outcome of the investigations occurred | ISZE requested IAST to formalise outcome of ISV (Sweden) engine hood protector complaints. IAST shared that during ISV meeting (Mainz, June 2026) that ISV requested to schedule 3-party meeting (ISA, IAST and ISZE) to understand final outcome of Engine hood protector claims. | Claim Engine hood protector (cracking): No update received from IAST | re Increase packaging solutions: Saida checked incomming IAS container arrival (Apr 29).enclosing mix goods.Container fill rate was good and Saida to continue observe future arrivals. Re Engine hood protector claims (crack), no update received during April. | ISV | 88.2 | K EUR | LS | 12.8 | K EUR
| IAST Cooperation and Efforts | Expend the range IAST survey result (April-May; Saida = PIC) IAST Action plan incl Timeline (Aug-Sept) Follow up readiness (Sept-Mar) | Apr - Mar | SZ/DW | G | X | G |  |  |  | X | X | X | X | X | X | ■■□□ Started | [11 empty] | ISZE combined all DB input and shared survey summary to IAST. | ISZE could see possitive outcome on sending kind reminder for DB to edit IAST survey. ISZE is working on the summary (June completion) | Upon receiving IAST survey mid-April, ISZE send out to all LCV distributors. Currently 3 DB'rs responded. | PP | 54.2 | K EUR | ROM | 11.1 | K EUR
| Local Accessories | Local sourced accessories sales Expend the range Navco: Tailgate remote lock and Replacement bulbs Explore ARB accessory | Apr - Mar | DW | X |  | X | Y | X | X | X | X | X | X | X | X | ■■□□ Started | Local accessories sales Dec23: Total amount 15.5 EUR or 5% of monthly invoice amount. Top sellers InfoTainment (11.9K EUR), Mobile Charger (0.8K EUR) | Higher profit | Local accessories sales: Profit on November sales of local accessory was 31.4%. Top sellers Tailgate down assist (8.2K EUR), Wheel nut indicator (1.8K EUR) | IBX | 56.7 | K EUR |  | IBX | 23.8 | K EUR | July update: During trial fitments, supplier Navco concluded that modification of Tailgate remote lock bracket is necessary. During August another trial to be scheduled | ISZE to schedule meeting with Navco (July) this to understand Navco stutus on Tailgate remorte lock and LED replacement bulbs |  | Navco shared that with assistance of IBX, a vehicle is offered for trial fitment of LED replacement bulbs (H4 & H7) as well for Tailgate remote lock. During May, the trial fitment details to be shared. | RSA | 43.8 | K EUR | GZ | 8.6 | K EUR
| Target local accessories sales | Monitor share vs TTL Invoice target as well profit margin | Apr - Mar | DW | G | G | G | G | X | X | X | X | X | X | X | X | ■■□□ Started | ISZE total CY23 Invoice amount for local accessories: 365.5K EUR (cost 303.6K EUR) = margin 16.9%, 10.5% share vs CY23 total invoice amount, much higher compared to 5+7 Sales Plan 2023. | [9 empty] | MTD and YTD results strongly attributed by Tow bar and Tow bar harness sales. ISZE fitting issue of Skid plates for MY25 and MY26 are pending. ISZE aksed manufacturer where in Germany trial fitment takes place, this to allocate suitable vehicle (ISD has support from ISD). | MTD invoice result local accessories: € 45.8K Q1 invoice result: € 309.7K vs TTL of € 987.6K, this represents 31% Gross margin Q1 (MAP): local accessories: 19% Vs Gross margin of APR+MAY (20.8%), shortfall is allocated to June Shutter lid sales (€ 11.8K) which having lower margin. | MTD sales result: € 86.9K YTD sales result: € 263.9K vs TTL sales amount € 791, represents 33% share. YTD sales result € 263.9K results to current gross proft (MAP) of 20.8% | ISZE local accessories business FY27 started with a surplus as MTD local accessories sales resulted to € 177K with proft of 19% From € 406K invoice result, local accessories reprensents 43% share Vs April 2025 result of € 96.4K with profit of 17%,and from TTL invoice amount represented 39% share.
| Key Account Management | Isuzu Companies ITUK + Isuzu East Aftica (IEA) | Apr - Mar | DW: DW; H1 JUL G: G; H1 AUG X: X; H1 SEPT X: X | ■□□□ |  |  | ITUK placed new orders of Wheel nut indicators | IUK | 33.6 | K EUR |  | RSA | 22.4 | K EUR | ISZE invoiced 300x Rubber mats required for urgent delivery (€ 16K). Remaining ITUK backorder are related to P700 rubber mats. ISZE forewarded Kenian company interest in Isuzu products to IEA. | ITUK requested ISZE calculating Airfreight cost for 300x rubber mats. MTD order result (€ 52.5K) includes initial order of P700 Rubber mats YTD sales result (€ 28.3K) is higher vs FY26 YTD result (€ 15.4K). Due to strong YTD result, ISZE increased FY27 sales target. | ITUK shared to place initial P700 Rubber mats order early June. ITUK shared no need for P700 Radio conversion harness 16P-14P (PN 1867240670)
| Key Account Management | IUK (IM Parts) | Apr - Mar | [13 empty] | ■□□□ | No order was issued by IUK during December. During face 2 face meeting (Dec 14th) with IUK, IUK requested 3% discount on fast moving accessories Tailgate down assist and crew cab bed liners. As well support in special prices for accessories to be shown at dealer conference (Feb 1st) eg Elysium canopy and very low price for give-away of model cars. | Efforts to increase sales | IUK placed replenishment order duirng 2nd half of November including 735x Bed liners (84K EUR) and 700x Tailgate slow down assist (27.4K EUR). | RSA | 21.6 | K EUR |  | DK | 7.3 | K EUR | Besides end June replenishment order (€ 146K), ISZE invoiced earlier Backorders | IUK replenishment order was placed on 30 June (€ 146K). IUK invoice result of € 2K is related to BO invoicing. | ISZE scheduled face to face meeting (3 June), joint meeting with IAS (location IUK office) and as well dealer visit (4 June) Main goal from these meetings is to understand IUK local sourced accessories range and potential sales opportunities for ISZE (incl accessories for future D-Max models, to be presented by IAS) | IUK April 2026 order amount resulted € 90.5K, in comparision to April 2025, surplus noticeable of € 78.3K. On average, IUK accessory stock value amounts to £ 2.6M, of which ISZE accessories stock share is at £ 700K including Elysium canopy overstock which amounts to £ 92K. IUK is currently running campaign to clear Elysium canopy stock | bar: DW to H2 MAR X
| SPA IUK Minutes visit | IUK (IM Parts) Special edition Minutes visit; FY & MTD result | Apr - Mar | [13 empty] | ■□□□ | IUK to issue special edition names STEEL incl V-Cross accessories Over fender set and RUP extentions and as well customized accessories eg Carpet mats. Project QTY = 300 units SOS April 2024. IUK did not place the order of V-Cross accessories during December. | [10 empty] | During on site meeting (3 June), IUK presented CY26 D-Max registration plan which illustrates negative growth of 54% (from CY25 result, 4849 units). Postiive affect on accessory sales/unit, CY26 YTD result shown nearly £ 2900/ unit vs £ 2200/ unit during CY25. The growth comes from IUK local accessory line-up and as well more accessories are fitted at PDI. |  | FY27 MTD invoice result € 142.3K, a surplus of € 26.5K is noticeable vs April 2025 Surplus is subjected to, invoicing Tow bar harness sets (€ 107.8K) | bar: DW
| Key Account Management | Others: | Apr - Mar | [13 empty] | ■□□□ | [10 empty] | PP: Petros complaint about ISZE tow bar unable to fit onto MY26 regular cab. With assistance of IBX, ISZE is hoping to allocate D-Max in order for GDW to conduct proper investigation. | During IMIE meeting, ISZE understood that Norway economy is not good, more building companies getting out of business. Outlook, lower vehicle sales that affects accessories sales to RSA | ISV MTD order amount (€ 177K), Over fender share (€ 93.2K) IRE: ISZE shared updated P700 RHD accessories range, incl RHD BSIS bracket and Radio Conversion Harness 16P-14P | FY27 Invoice result (excluding IUK) amounts to € 263.4K vs FY26, (€ 117.9K) an increase is noticeable of € 145.5K. The variance are mainly allocated to IBX (+ € 63.6K), followed by ISV (+€ 23.5K), RSA (+€ 16.9K) and ISD (+€ 16.3K) | bar: DW to H1 JUN Y; H2 NOV X
| SPA Activities Others | Special editions; Fleet deal, Tender business FOC sample order KIMA fleet deal (sales expected June 2026) | Apr - Mar | DW: DW; H1 JUN Y: G; H2 DEC X: X | ■□□□ | ISD placed V-Cross accessories dark grey, total amount 65.5K EUR, still about 98.5K EUR to be ordered (235x Over fender set). RSA placed advanced order for delivery during Feb. Isuzu Sweden placed advanced orders up to April incl 500x Rubber trays. | Efforts to increase sales | Isuzu Sweden placed advanced orders for delivery Jan-April 2024 incl 540x UR CRW Bed liners (approx 67K EUR) | CY 2023 invoice totals | [6 empty] | ISZE completed KIMA accessory order for fleet deal. ISZE is waiting for full container load to invoice subjected order. | KIMA: Accessories order € 9.6K was received end June. |  | KIMA shared that upcomming accessory order for June delivvery is subjected to change. This upcomming order is related to the fleet deal started FY26. The changes to be discussed during Teams mtg (TBA)
| Localisation | Increase local accessories: Expend the range with current partners | Apr - Mar | [13 empty] | ■□□□ | 👍 comments see below | Higher profit | CY 2023 YTD local accessories sales amounts to 346.9K EUR vs total 3,177.4K EUR achieving 10.7% share. YTF Profit % is 16.8% | bar: DW
Local | GDW | Other tow bars besides Flange type | Apr - Mar | [13 empty] | ■□□□ | re Skid plats: ISZE informed ISD and Imotors special price for tenders. ISZE shipped 2x skid plate samples to ISD. Re Tailgate down assist: No delivery took place during december affecting IUK vehicle preparation process. re Tailgate up&down assist: ISZE shipped samples to DK, Poland | Efforts to increase sales | During joint meetings at ISZE office, ISD informed that Rival skid plates are suitable and will need some samples to make trial fitment at a car which is heavily used at a mining comp. As well Imotors informed that there might be 2x tenders for skid plates. ISD potential: 200-300pcs. Imotors potential 25-75pcs | bar: DW
LOCALISATION NEW IDEAS | Localisation | Increase local accessories line up and sources. Take actions towords future concepts. | Apr - Mar | DW: DW/HT | ■□□□ | ISZE shipped samples for trial fitment at distributor side. ISZE also asked quotation for full sealed harness (for Scandinivan countries). | Efforts to increase sales | ISZE shipped samples for trial fitment at distributor side.
| Truckman (An ARB company) UK | 5pc Bed liner; Bed rug | Apr - Mar | DW: DW/HT | ■□□□
| Navco (N) | Idea: New Mobile Charger (armrest compartment) , Electrical side step Bulb lights kit | Apr - Mar | [13 empty] | ■□□□ | No update received | Efforts to increase sales | Update was received on MY24 InfoTainment syst. Since the information was a bit to technical, ISZE need more information starting with scheduling a teams meeting. | bar: DW
D | Detail steps new ideas | Method steps introducing new local sourced items | Q3 2022/ end 2022 | DW: DW / HT | ■□□□
E |  | Check sales potential | Q3 2022 | DW | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
T |  | Check DB conditions | Q3 2022 | DW | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
A |  | Check commen suppliers + RFQ to suppliers | Q3 2022 | DW/ HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
I |  | Reporting - Most appealing ones | Q3 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
L |  | Readiness plan Overview Local Supplier, Checking spec | Q4 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
|  | Sample | Q4 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
S |  | Sample delivery/ fitment | Q4 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
T |  | Review Sample fitment | Q4 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
E |  | Review Conditions | Q4 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
P |  | Decision making | Q4 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
S |  | Order/ No order | Q4 2022 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
|  | Face 2 face meetings (Joint & Indiviual) to verify mutual understanding and seek next project for commercial growth | Q4 2021 | DW/HT | - | - | - | - | - | X | - | - | - | - | - | X | ■□□□
SALES SUPPORTING |  | 2024 Fairs & Exhibitions Automechanika (DE) September 2024 SEMA (USA); November 2024 | Apr - Mar | DW: DW/HT; H1 SEPT X: X | ■□□□ | IUK Dealer conference (Feb 1st) Geneva Int.Motor Show (26 Feb - 3 Mar 2024) Geneva, Swiss Commercial Motor Show Birmingham (23-25 April 2024), UK |  | Thailand Int. Motor Show (1-11 Dec) Geneva Int.Motor Show (26 Feb - 3 Mar 2024) Geneva, Swiss Commercial Motor Show Birmingham (23-25 April 2024), UK
| 3D/ AM | BSIS bracket ,RHD development Potential 3D tool is required | Apr - Mar | DW: DW; H1 MAY Y: X; H1 JUN Y: G; H1 JUL G: G; H1 SEPT X: X | ■□□□ | [10 empty] | ISZE promoted LHD and RHD BSIS bracket (P700 N-Series). First sales result expected during August. | ISZE received stock of LHD BSIS bracket. Early July, ISZE to set sales pricing for both, LHD and RHD BSSIS bracket | ISZE received RHD BSIS brackets from Midi. | ISZE placed order at Midi (final badge of 40x RHD BSIS bracket).Next step to prepare when initial QTY of 40x are sold.
| Tool | Power BI (PBI) for Accessory procurement | Apr - Mar | [13 empty] | ■□□□ | bar: DW; H1 SEPT X to H2 MAR X
| ISZE Marketing activities | Bulletins, Introduce new items, Campaigns; etc | Apr - Mar | DW/SZ |  | X | X | X |  | X | X | X | X | X | X | X | ■□□□ |  | Efforts to increase sales | [8 empty] | ISZE send notification informing DB's that all accessory informaiton is available at Sharepoint. As no unsolved issues are reported, ISZE to send out during September, DB 3-month evaluation | ISZE IT dept is working on new tool (Sharepoint) for DB to access and download all accessory information. During July ISZE to send the access details to all DB contacts
IAS COLLABORATION
| Collaboration with IAS | [15 empty] | ■□□□
| Sales | General sales topic incl claims | Apr - Mar | DW: DW/HT | ■□□□ | For MY24 D-Max accessories, pending topics: complete PN information for MY24 bed liners and canopy (all types). As well instruction manuals documents, TUV document for MY24 canopies and bed liner hooks. And high resolution images for all MY24 accessories. | Future sales affected | For MY24 D-Max accessories, ISZE is still waiting on IAS clear explanation re Bed liners. ISZE provided input during IAS visit at ISZE (end September) but no status is received from the actions that are needed..
|  | Mgmt Teams Meetings / co-visits | Apr - Mar | DW: DW/HT/MH | ■□□□ | Next management meeting (Teams) is scheduled on Jan 16th |  | Next management meeting (Teams) is scheduled on Dec 13th
| Next step | Improve market intelligence (develop suitable products for EU market) by continuesly informing DB'ers needs | Apr - Mar | DW: DW/HT | ■□□□
| ACC parts supply improvement (Shorten lead times) | Follow up on improvement steps and related actions, from IAS methology | [14 empty] | ■□□□ | Still gaps in receiving buffer stock at IAS side. ISZE is unsure if sufficient effrots are made to avoid no stock for +1 month. | IAS to improve | Still gaps in receiving buffer stock at IAS side. ISZE is unsure if sufficient effrots are made to avoid no stock for +1 month.
| Buffer stock & Container filment | Monitor Container filment | Apr - Mar | DW: DW/HT | ■□□□ | From January 2024, to change topic name IAS MY24 preparation (incl buffer stock progress, standard lead times, etc)
|  | RG progress Buffer stock progress | Apr - Mar | DW: DW/HT | ■□□□ | Although IAS have pre-ordering components of bed liners, currently situation is that Bed liner deliveries showing delays. Resulting that distribiutors delivery expectations are not maintained. FYI: ISZE placed ordes well ahead. Only 1 container to arrive during January (2x pallets UR crew + 2x pallets OR crew and 2x pallets UR EXT). | IAS to improve | Although IAS have pre-ordering components of bed liners, currently situation is that Bed liner deliveries showing delays. Resulting that distribiutors delivery expectations are not maintained. FYI: ISZE placed ordes well ahead.
[17 empty] | ■□□□ | From january 2024, to change topic name IAS MY20~MY23 preparation (incl buffer stock progress, standard lead times, etc)
♦Expend the range
| ♦ISZE ideas new Local accessories |  | Reason | [13 empty] | Status July | [10 empty] | July Activity Report | June Activity Report | May Activity Report | Comment
|  | 3D Mat | No durt at vehicle floor mat | [13 empty] | IAST/other | [11 empty] | ISZE/IAST could see sample 3D Mat during IUK dealer visit (4 June) |  | IAST to foresee SOS Q1, CY27
|  | 2nd line Carpet mats | IAS unable to reacht to IUK spot demand
| MY28 IAST Acc | Over fender, Canopy, Tow bar | Full model change | [13 empty] | IAST | [11 empty] | On 4 June IAST received IUK input on accessoires for new model | IAST shared survey, which IAST to use first DB with IUK (4 June)
|  | ALU Canopy | Astara comp (ISD & IBX) already considering | [13 empty] | Carry over | [11 empty] | During IUK visit, ISZE have seen samples of IUK ALU canopy. | IUK shared sales result Winbo shutter lids, 400 units, this after SOS 9 months ago | Deskstudy FY26 - Alu canopy supplier locations: South Africa, Thailand and Germany (IUK= China)
|  | EXT Cab canopies | IAS will not consider this | [13 empty] | New
| Navco | Replacement bulbs H4 & H7 to LED | [14 empty] | Plan | [10 empty] | Trial fitment to be announced (during August at Dealer De Witte) | As uodates remain pending, ISZE to schedule meeting with Navco. | Navco update in sending trial fitement result is pending | During May/ June trial fitment results are expected
| Navco | Tailgate lock remote locking | Many DB approached ISZE | [13 empty] | Navco/other | [10 empty] | During trial fitment 23 July, small difference occurs between MY25 and MY26 Tailgate lock system. Minor modification necessary of Tailgate remote lock bracket. Next trial fitment during August (TBA). | IUK shared during F2F Meeting to have local alternative for Tailgate remote locking at £55. | Navco update in sending trial fitement result is pending | During May/ June trial fitment results are expected
| IML New accessories P700 RHD |  |  |  | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Status July | [10 empty] | July Activity Report | June Activity Report | May | Comment
|  | IASJ: P700 Accessories | SOS RHD markets | [13 empty] | Started | [11 empty] | ISZE invoiced RHD P700 accessories to ITUK (€ 11.6K) | ITUK to send first order (Rubber mats) during June | bar: June
|  | ISZE: P700 BSIS Bracket RHD | Development to SOS | [13 empty] | Started | [10 empty] | ISZE promoted N-series BSIS bracket. ISZE understood from DB responses: GZ & LS to place orders. LS order of 20x is received. IMOT placed order to Midi (55 units) IRE: Unsure how IRE to proceed ITUK/IMOT: Looking for F-series spare part that covers all bracket sizes. ISZE informed to order first from available stock of each size. | ISZE received LHD BSIS brackets from Belgium manufacturer | ISZE received RHD BSIS brackets from Midi. | ISZE issued order to MIDI for RHD truck BSIS Bracket | bar: June to July
[5 empty] | G | Y | R | -
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R
G
Delayed, non recoverable
Y
Delayed, but recoverable
On schedule
R

## Sheet1
# | Order receipt | QTY | Invoiced QTY | Date
1 | 2026-04-20 | 2 | 2 | 2026-05-08
2 | 2026-04-30 | 96 | 96 | 24 July Completed
3 | 2026-05-11 | 28 | 28 | 01 June completed
4 | 2026-05-13 | 96 | 0
5 | 2026-05-13 | 96 | 0

## 2018 (hidden)
2025
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
ITUK(TVS) | 262.28 | 425.8 | 478.5 | 219.92 | 511.5 | 608.79 | 745.2 | 1168.92 | 471.12 | 1055 | 366.47 | 566.16
IML | 272424.96 | 227153.59 | 257393.85 | 174924.64 | 360193.88 | 284968.85 | 244235.11 | 264184.8 | 197102.67 | 317226.1 | 302506.64 | 281549.08
UMI | 207513.99 | 274113.91 | 210045.38 | 92693.61 | 124767.01 | 147430.42 | 184271.12 | 76980.32 | 221956.34 | 134869.96 | 105369.16 | 250885.18
UTI | 2025 JAN: 1.74; 2025 FEB: 1.45; 2025 AUG: 1.16
ISZ RUS | 51936.84 | 87850.14 | 90518.1 | 79971.57 | 99166.05 | 109757.88 | 110952.56 | 80432.29 | 106977.9 | 93717.66 | 83511.55 | 67522.09
IBX | 114722.57 | 87583.79 | 106321.75 | 94996.19 | 104744.02 | 118022.84 | 113593.56 | 100234.69 | 93463.2 | 97793.72 | 113299.45 | 84301.72
ISD | 9554 | 14701.05 | 4979.52 | 3776.23 | 3377.05 | 13560.47 | 39093.65 | 15689.55 | 14829.66 | 25602.05 | 8225.23 | 20601.35
OTHERS | 233270.01 | 238277.4 | 297896.77 | 239312.47 | 178491.3 | 233870.94 | 201629.94 | 272639.56 | 237090.3 | 314020.25 | 250298.87 | 207138.52
ITUK(TVS) | 230504.48 | 320544.27 | 353643.58 | 281026.11 | 358407.54 | 401022.91 | 356682.43 | 349756.46 | 297470.7 | 394579.25 | 284011.92 | 222710.25
IML | 51781.69 | 28681.35 | 39374.02 | 38701.68 | 59591.18 | 28753.97 | 39215.39 | 57657.68 | 54866.4 | 36953.73 | 45482.68 | 43685.86
UMI | 25023.62 | 36433.18 | 40649.89 | 16076.89 | 24881.89 | 26068.64 | 23901.19 | 26062.73 | 26822.39 | 25410.23 | 29978.42 | 36195.13
UTI | 143289.89 | 190499.08 | 137245.35 | 145388.93 | 92714.15 | 179720.08 | 213703.41 | 179637.4 | 181287.1 | 91586.23 | 222052.25 | 148930.12
ISZ RUS | 24087.4 | 20210.32 | 29892.45 | 17098.49 | 22106.19 | 23211.34 | 20008.95 | 21868.64 | 24514.3 | 28390.68 | 22375.7 | 16333.41
IBX | 27116.82 | 22900.13 | 30686.68 | 31208.19 | 30392.71 | 31411.61 | 22007.03 | 30702.59 | 22409.4 | 28861.02 | 29411.53 | 17134.09
ISD | 307617.23 | 672517.66 | 138185.44 | 577423.17 | 241509.27 | 113793.09 | 431812.59 | 279787.83 | 276540.97 | 596646.27 | 317394.58 | 124916.46
OTHERS | 172281.58 | 132806.81 | 164528.42 | 150257.71 | 142242.33 | 186784.35 | 151013.13 | 150193.38 | 172480.93 | 169315.85 | 171400.31 | 165338.68
ISZR (FE) | 317912.41 | 74726.29 | 180818.55 | 83037.95 | 81832.93 | 91728.35 | 67204.46 | 12136.4 | 97383.68 | 48375.44 | 120358.71 | 177195.63
TH | 889686.39 | 930107.13 | 967633.87 | 685894.63 | 871250.81 | 908220.19 | 894521.14 | 811331.29 | 871891.19 | 984284.74 | 863577.37 | 912564.1
JP | 1299615.12 | 1499319.09 | 1115024.38 | 1340219.12 | 1053678.19 | 1082494.34 | 1325548.58 | 1107803.11 | 1153775.87 | 1420118.7 | 1242466.1 | 952439.63
TTL parts amount | 2189301.51 | 2429426.22 | 2082658.25 | 2026113.75 | 1924929 | 1990714.53 | 2220069.72 | 1919134.4 | 2025667.06 | 2404403.44 | 2106043.47 | 1865003.73
Tranport surcharge | 69546.13 | 67541.69 | 67313.85 | 65562.33 | 66639.77 | 72207.64 | 62599.12 | 71006.58 | 61076.28 | 77383.17 | 68052.28 | 54561.81
Others | 43530.6 | 5504.74 | -28777.23 | 1185.21 | 4730.36 | 7353.56 | 13977.47 | 5407.11 | 54829.57 | -126789.43 | -84875.28 | -151332.22
GRAND TOTAL | 2302378.24 | 2502472.65 | 2121194.87 | 2092861.29 | 1996299.13 | 2070275.73 | 2296646.31 | 1995548.09 | 2141572.91 | 2354997.18 | 2089220.47 | 1768233.32